## Slide 1: Stop TB Partnership Task Force on Retooling
Nina Schwalbe & Vinand Nantulya Co-Chairs
Progress report

## Slide 2: Presentation outline
Definition and rationale for Retooling Task Force
Terms of Reference for the task force
Composition of the task force
Framework document
The Work plan for 2007
Budget for 2007
Decisions points requested

## Slide 3: Challenge to the TB community
Adoption and timely introduction of new tools for TB control as they become available will require coordinated action by the Stop TB community at global and national levels
The Board’s response
The Coordinating Board at its meeting in Abuja, April 2006, decided to approach this challenge by establishing the Task Force on Retooling

## Slide 4: “Retooling” is defined as..
The process of preparing for Adoption and Introduction of New Diagnostics, Drugs and Vaccines in TB control
Notes: Implementation?

## Slide 5: The TORs for the Task Force (endorsed by CB at its Abuja meeting in April 2006)
Develop a work plan and time lines
Consolidate and share information from tools working groups (timelines, milestones, etc)
Create dialogue among stakeholders
Facilitate mobilization of resources

## Slide 6: Terms of Reference (cont’d)
Consolidate lessons learned from other innovations
Fast track incorporation in WHO and national policy
Enhance communication among working groups
Facilitate introduction of operations research and generate evidence around new tools

## Slide 7: Task Force Members
DOTS Expansion
Ikushi Onozaki
Léopold Blanc
Aziz Mohammed (laboratory subgroup)
Drugs
Christy Hanson
Nina Schwalbe (co-chair)
Diagnostics
Andrew Ramsey
Vinand Nantulya (co-chair)
Vaccines
Ulrich Fruth
TB/HIV
Barbara Laughon
TB Community
Javid Syed
TB & Poverty
Birte Holme Sorensen
ACSM
Carole Francis
MDR-TB
Karen Weyer
TDR
Philip Chukwuka Onyebujoh
NTP Managers
Saidi Egwaga
Lindiwe Mvusi
GDF
Robert Matiru
Secretariat
Rachel Bauquerez
Sarah England
Notes: Currently 17 members (plus Secretariat).
Working Group members, designated by chairs and key sub groups (laboratory, GDF, TB&Poverty)
National TB Program Managers from high- burden countries
Stop TB Partnership Secretariat (as secretary)
To be include in the future : Other relevant WHO departments, NTP Managers from another regions and NGOs

## Slide 8: First deliverable of Task Force
“New technologies for TB control: a Guide on their Adoption, Introduction and Implementation”

## Slide 9: Objectives of the guide
Provide a common framework to discuss the adoption of new tools for TB control;
Identify some key issues that need to be addressed to accelerate the adoption and implementation; and
Provide guidance on what actions are needed for adoption, access and proper use of tools by the community as they become available.
Notes: During our first face-to-face meeting in Geneva in July 2006, the task force agreed as first concrete step to produce the retooling guide. The task force commissioned MSH to draft the document, under guidance from task force core group (supported by weekly teleconferences)
The objectives of the guide were….(on the slide). The term "available" varies depending on the product and will be explained you in the next slide.
Completion of a draft guide at Paris conference for presentation at this Coordinating Board meeting

## Slide 10: Structure of guide
Provides a common framework to discuss the adoption, introduction and implementation of new tools
Identifies key challenges and proposes actions to facilitate appropriate and timely adoption and implementation of new technologies.
  Engaging stakeholders early from beginning of policy analysis through adoption, to implementation
  Advanced planning and preparation globally and nationally
  Conducting operations research to guide the adoption, introduction and implementation
Provides overview of technical and operational considerations for global and national levels

## Slide 11: Appendix
Provides an overview of selected new medicines, diagnostics and vaccines in the pipeline;
Lists key actions for the adoption and implementation of each technology category;
Provides illustrative generic timeline for adoption, introduction and implementation;
Lists key readings that provide more detailed discussions of the issues and road maps

## Slide 12: Selected new diagnostics products in the pipeline
Notes: For diagnostics availability (set as AA on this slide) is after demonstration studies.
DP is demonstration phase
Alreay in used at country level

## Slide 13: Pipeline: New drugs
Notes: For drugs and vaccines it is after Phase III clinical trials

## Slide 14: Pipeline: New vaccines

## Slide 15: KEY ACTIONS FOR NEW ANTI-TB DRUGS (ILLUSTRATIVE)
Issues | Key Actions | Technical/ Operational Lead | Estimated Timeline | Resource Requirements
Global policy development | Engage key stakeholders and facilitate the discussion at global level on the inadequacies of existing medicines and strategies and the need and potential strategies for change |  |  | 
 | Ensure partners and stakeholders have a common understanding of the process and mechanism for decision making for policy development on adoption of new tool |  |  | 
 | Assemble and submit information on the risks and benefits of the new tool to WHO |  |  | 
 | Scientific and technical guidance for the decision making group developed by WHO’s Strategy and Technical Advisory Group for Tuberculosis ( STAG) and the need for additional studies identified |  |  | 
 | Analyze the capacity of health systems in member countries to adopt, and appropriately manage and use the new tool; identify needs for further studies/operational research |  |  | 
 | Review scientific and technical guidance and study results and decide to develop a new policy to recommend adoption of the new tool (or not) |  |  | 
 | Develop, endorse and communicate the new policy |  |  | 
International TB guidelines and materials | Determine costs and responsibilities for updating and dissemination of international guidelines and associated technical materials and tools |  |  | 
 | Update and print guidelines; develop, budget and implement a strategy to communicate recommendations |  |  | 
 | Submit an application to add the new tool to WHO EML; communicate decision to country-level |  |  | 
 | Identify, update and field test training materials and other technical tools |  |  | 
 | Develop, field test and disseminate an operational guide and a package of tools to assist countries and decision makers to adopt and implement the new recommendations |  |  | 
Registration | Determine approaches to assist countries to register the new tool |  |  | 
WHO prequalification | Inform manufacturers of the requirements for WHO prequalification of the new product; provide information on an acceptable dossier |  |  | 
 | Encourage manufacturers to begin the process of assembling the dossier and submitting the application in good time |  |  | 

## Slide 16: TIMELINE FOR ADOPTION AND IMPLEMENTATION (ILLUSTRATIVE)

## Slide 17: Work plan for 2007
Finalize, edit, design and print the document
Develop and implement a plan for dissemination of the document
Develop additional documents and guidelines critical for retooling, including:
  Guidance on stakeholder engagement;
  Updated the pipeline chart;
  Retooling monitoring and evaluation framework;
  Illustrative timelines for post regulatory process;
  Recommendations for introduction of specific new tools and;
  Revised and expanded checklist on introduction (annex 2-4 of current document).

## Slide 18: Dissemination plan to include
Presentations and distribution of hard copies at annual meetings of working groups and key global and regional conferences and meetings
Presentations to donors that fund both development of tools and programs globally
Posting the guide on web site of Stop TB Partnership and partners website

## Slide 19: Budget estimates for 2007
Request USD 150,000 funding in support for:
  Meetings (2-3 face-to-face meetings, next one is in New York January 22-23)……USD 50,000
  Subcontracting services to develop other documents.......USD 50,000
  Design and print retooling guide….USD 25,000
  Dissemination of retooling guide….USD 25,000
TDR committed USD 20,000

## Slide 20: Acknowledgement
Funding support for this initial work was provided by
  USAID
  FIND
  Global Alliance for TB Drug Development
  TDR
  Stop TB Partnership*
MSH Team
  David Lee
  Evan Lee
  Helena Walkowiak
  Naranjan Konduri
* Provided travel for high burden country representatives to the Washington meeting and Secretariat

## Slide 21: Decisions requested
Endorsement of the guide to implementation of new tools
Endorse the 2007 work plan of the task force
Help brainstorm on the dissemination plan for the guide
Ensure all working groups are represented on the task force